# Fabric Capacity Policies

Migration guide

Version 1.0 - 14 October 2026

Contents

# Scope of this document

This guide is the operational how-to for the one-off cutover that brings the existing Fabric estate under the Fabric Capacity Policies solution. It tells the person running the cutover which flow to run in each phase, with what input, what to check afterwards, when to stop and how to undo it.

It does not explain how the four MIG_ flows work - that is in the Architecture document section 5 - and it does not repeat their build detail. Day-to-day monitoring after cutover is in the Error handling and monitoring guide.

# 1. What the migration does, and why it is phased

The migration gives every eligible capacity a policy set, fills it with rules from Dataverse, and only then switches enforcement on. It uses four manual flows in the UBS Workspace Provisioning solution, run by hand in a fixed order:

| Flow | Phase | What it does |
| --- | --- | --- |
| Fabric Pol - MIG_RegisterAllCapacityPolicySets | 1 | Creates one policy set per Active F-SKU capacity - no rules, deactivated - and a Capacity Policies row with Status = Inactive |
| Fabric Pol - MIG_InitializeCapacityPolicySet | 1 | The child flow the register loop calls once per capacity. Never run it on its own |
| Fabric Pol - MIG_RebuildAllCapacityPolicies | 3 | Publishes rules 1-3 to every registered policy set. Still deactivated |
| Fabric Pol - MIG_ActivateAllCapacityPolicySets | 4, 5 | Report mode is the dry run; Activate mode puts the policy sets into force |

Every published policy set carries the same three rules:

| Rule | Who it is for | Effect |
| --- | --- | --- |
| Rule 1 - Deny all, Power BI only | Every workspace on the capacity. Always present | Power BI items only |
| Rule 2 - OAP workspaces, approved item types | Workspaces marked ubsppcoe_oapenabled in the platform team's inventory | Power BI plus the item types in Policy Item Types |
| Rule 3 - Exceptions, allow all | Active rows in Policy Exceptions | Any item type |

Everything before Phase 5 is inert. A policy set with no rules, or with rules but deactivated, changes nobody's access. A wrong run in Phases 1-3 is undone by deleting the policy sets from the holder workspace and the rows from Capacity Policies, and nobody notices.

Phase 5 ends that. An activated policy set with rule 1 and nothing else stops all governed item creation on its capacity; only Power BI items are unaffected. That is why the phases are separate runs with a review gate in front of activation: the gaps between them are where mistakes are caught. Do not compress the phases.

All Fabric calls are made as the workspace provisioning service account through the HTTP with Microsoft Entra ID (preauthorized) connector. Report mails go to the PolicyMailRecipients environment variable.

# 2. Pre-flight checklist

Nothing in this section changes anything. Every item is cheaper to fix now than to discover in Phase 5. The flows, tables and environment variables are assumed to be deployed already, per the Deployment guide.

## 2.1 Flows

| # | Check | Why |
| --- | --- | --- |
| F1 | Turn off Fabric Pol - InitializeCapacityPolicySet, Fabric Pol - AddWorkspaceToPolicy, Fabric Pol - RemoveWorkspaceFromPolicy and Fabric Pol - RebuildOnExceptionChange | They fire on Dataverse row changes with nobody pressing anything - including on the Policy Exceptions rows seeded in Phase 2 |
| F2 | Leave Fabric Pol - DeleteCapacityPolicySet on | A Node row soft-deleted between registration and activation moves its Capacity Policies row to Deleted or Suspended, which keeps it out of activation. If it cannot be on, see Phase 5.1 |
| F3 | Leave Fabric Pol - RebuildCapacityPolicyRules on | It is a child flow; a flow that is off cannot be called as one |
| F4 | Fabric Pol - MIG_RebuildAllCapacityPolicies off until Phase 3 | An enabled manual flow is one stray button press from publishing rules before exceptions are seeded |

## 2.2 Identity and permissions

| # | Check | Needed for |
| --- | --- | --- |
| I1 | The Fabric connection in each MIG_ flow is signed in as the workspace provisioning service account, not a personal account left over from a rehearsal | Every phase. A wrong account fails quietly, as a short capacity list |
| I2 | The account is Contributor on the holder workspace | Creating policy sets, Phase 1 |
| I3 | The account is Capacity Admin on every capacity to be governed | Seeing the capacity at all in Phase 1, and activating it in Phase 5 - the first time the permission is exercised at scale |

Both permissions are granted directly to the account; there is no service principal, app registration or client secret (see the Architecture document section 6).

## 2.3 Tables and seed data

| # | Table | State required |
| --- | --- | --- |
| T1 | Capacity Policies | Exists, empty or nearly so. No rows left over from testing - a leftover row makes that capacity answer AlreadyExists and be silently skipped |
| T2 | Policy Item Types | Seeded and active: 14 rows from the seed list of item types (see the Deployment guide section 3, Step 3), Active = Yes on all of them. An empty or inactive table makes rule 2 carry an empty item.type list, which Fabric rejects |
| T3 | Policy Exceptions | Exists. Seeding happens in Phase 2 |
| T4 | Holder workspace in Fabric | No policy sets left over from testing - a leftover set causes a name collision in Phase 1 |

Policy Drift is not part of the solution and must not exist.

## 2.4 Environment variables

All seven need a Current Value, not only a Default Value. A missing one fails at runtime with The workflow parameter ... is not found, once per capacity, all the way through a run.

| Variable | Value for the cutover |
| --- | --- |
| PolicyHolderWorkspaceId | The holder workspace GUID |
| PolicySentinelWorkspaceId | 00000000-0000-0000-0000-000000000000 |
| PolicyMaxWorkspacesPerRule | 49 |
| PolicyMaxRulesPerPolicy | 50 |
| PolicyNamePrefix | pol_ |
| PolicyApiBeta | No while the API is in private preview; Yes once it is in public-preview beta (see the Architecture document section 8.6). Pointing the wrong way shows up as a 400/404 on every capacity with nothing naming the variable |
| PolicyMailRecipients | A semicolon-separated list, ideally one distribution group, read during the migration window. Read it off the variable - do not assume it is not still pointing at a rehearsal mailbox |

## 2.5 Estate checks

| # | Check | Why |
| --- | --- | --- |
| E1 | Duplicate capacity display names | Policy set names are pol_<capacity display name>, and Fabric rejects a duplicate with ItemDisplayNameAlreadyInUse. If there are any, append the capacity-ID suffix unconditionally in MIG_InitializeCapacityPolicySet Step 5a, where the policy set name is built |
| E2 | Where the holder workspace sits | If it is on a capacity this solution will govern, rule 1 will stop the solution creating policy sets in it, and its Policy Exceptions row in Phase 2 is mandatory. If it sits on a capacity with no ubsppcoe_Node row, nothing governs it. Decide which case applies now |
| E3 | Rollback tooling is reachable | Undoing an activation means deactivating the policy set with the Fabric REST call POST /v1/workspaces/{holder}/policySets/{id}/deactivate, made as the workspace provisioning service account (section 4; see the Architecture document section 8). To confirm: the tooling for making this call is not part of this handover, so confirm before Phase 5 that someone on the cutover can make it |

# 3. Phase-by-phase procedure

Each phase states what to run, what to check, the go/no-go criterion and how to roll back. Record the outcome of every phase in the sign-off checklist in section 6.

## Phase 0 - Pre-flight

Run: nothing.

Work through every row of section 2.

| Go | Every check in section 2 confirmed, and the holder-workspace decision (E2) recorded |
| --- | --- |
| No-go | Any check open. In particular, do not start Phase 1 with the wrong account on the Fabric connection |
| Rollback | None needed - nothing has changed |

## Phase 1 - Register

Run: Fabric Pol - MIG_RegisterAllCapacityPolicySets, manually. No inputs. Run it in tranches by cancelling from the run history.

- Start the run and check the candidate count. Let it reach Compose_eligible_count and read the value. If it is materially smaller than the estate, cancel. GET /v1/capacities only returns capacities the workspace provisioning account administers, so a short list means the wrong account or missing Capacity Admin - an identity problem, not a data problem.

- First tranche - five capacities. Cancel after about five iterations, then check by eye:

| Check | Where | Expected |
| --- | --- | --- |
| Policy sets exist | Holder workspace, Fabric portal | Five new items |
| No rules | Open one | Empty rule list |
| Not activated | Open one | Inactive |
| Rows exist | Capacity Policies | Five rows |
| Node populated | Open a row | A Node lookup, not blank |
| Status | Same row | Inactive |
| Counts | Same row | ubsppcoe_lastrebuild, ubsppcoe_rulecount, ubsppcoe_workspacecount blank |

- An activated policy set here is deny-all in force on a capacity nobody approved - the child still carries the BAU activation step. Stop and fix it. A blank Node means the lookup bind is wrong and the capacity can never be rebuilt: fix the bind, delete the rows and sets, start Phase 1 again.

- Second tranche - about 40 capacities. Re-run; registered capacities answer AlreadyExists and are skipped, so each run resumes where the last stopped. Check the noNode list is plausible rather than "everything".

- The rest. Re-run and let it complete (roughly 10 seconds per capacity, so 30-40 minutes for 200).

- Read the report mail. It goes to PolicyMailRecipients and is sent only when there is something in the noNode or failed list; the subject carries all three numbers. A cancelled tranche sends nothing, so check the holder workspace and the table instead.

| Bucket | Meaning | Action |
| --- | --- | --- |
| Registered | Created this run | None |
| No Node row | Active F-SKU in Fabric, but no live ubsppcoe_Node row - missing, or soft-deleted (ubsppcoe_statecode = 2) | Hand the list to the platform team. Nothing was created; these capacities are out of scope until a Node row exists |
| Failed | Duplicate name, permission, timeout | Fix, then re-run |

| Go | Failed is empty after re-runs; every row has Node populated and Status = Inactive; no policy set is activated; the noNode list is with the platform team |
| --- | --- |
| No-go | Short candidate count, any activated policy set, any blank Node, or failures not understood |
| Rollback | Delete the policy sets from the holder workspace and the Capacity Policies rows. Nothing else has happened |

## Phase 2 - Seed exceptions

Run: nothing. This is a data import into Policy Exceptions, and it must happen before Phase 3. Rule 3 is derived from nothing else.

- Prepare the exceptions list as a CSV import file (see the Deployment guide section 3, Step 4). Its headers are the Dataverse logical names. Delete its three EXAMPLE rows first.

- Add the holder workspace row first if section 2.5 E2 says the holder sits on a governed capacity:

| Column | Value |
| --- | --- |
| ubsppcoe_workspacename | The holder workspace's name, labelled so the row is never revoked by mistake |
| ubsppcoe_workspaceid | The GUID in PolicyHolderWorkspaceId |
| ubsppcoe_active | Yes |
| ubsppcoe_reason | Holds the policy set items. Excepting it prevents the policy system locking itself out |
| ubsppcoe_approvedby | The owner of this solution |

- The row only works if the holder workspace has a ubsppcoe_Workspace row under the Node of its capacity. Without one there is no rule 3 entry and no error. Ask the platform team if it is missing.

- Add the estate's existing exceptions - from the estate's current exceptions list, if the migration has one. Take its workspace_id column into ubsppcoe_workspaceid, set ubsppcoe_active to Yes, and copy reason and approver. Do not import capacity_id - the capacity is derived from the workspace's Node at rebuild time - but check that the two agree first: a mismatch is an exception that is about to move capacity on the first rebuild.

- Import through the maker portal: Tables > Policy Exceptions > Import > Import data from Excel, file type CSV. Leave the row key ubsppcoe_policyexceptionid unmapped.

- Check that every imported row reads Active = Yes. ubsppcoe_active defaults to No, and an unset flag is the usual reason an exception appears to do nothing.

If the estate has no exceptions and the holder needs none, skip this phase. Skipping it when there are exceptions is invisible: Phase 3 publishes without rule 3, and those workspaces become restricted at Phase 5 with nothing reporting it.

| Go | Row count matches the source list (plus the holder row), all Active = Yes, no EXAMPLE rows, holder workspace has its ubsppcoe_Workspace row |
| --- | --- |
| No-go | Any exception whose workspace is not in ubsppcoe_Workspace, or whose Node disagrees with the source exceptions list and nobody has decided |
| Rollback | Correct or remove the imported rows. Nothing has read them yet |

## Phase 3 - Rebuild

Run: Fabric Pol - MIG_RebuildAllCapacityPolicies, manually. Turn it on, use Run, then turn it off again. No inputs.

It rebuilds every Capacity Policies row with a policy set, oldest ubsppcoe_lastrebuild first, and stamps ubsppcoe_lastrebuild, ubsppcoe_lasterror, ubsppcoe_rulecount, ubsppcoe_workspacecount and ubsppcoe_exceptioncount. Still nothing is enforced - every policy set is deactivated.

Check afterwards:

- The mail. It is sent only when a capacity failed, with the failure count in the subject. A clean run sends nothing.

- The table. Every row has a recent ubsppcoe_lastrebuild and an empty ubsppcoe_lasterror. This is the only proof that a clean run finished.

- The portal. Open one capacity: rule 1 present, plus a rule 2 if it has OAP-enabled workspaces.

- An exception. If Phase 2 seeded any, open a capacity that has one: rule 3 present, with one condition and no item.type.

| Go | Every row has ubsppcoe_lastrebuild set and ubsppcoe_lasterror empty, or every remaining failure is understood and accepted |
| --- | --- |
| No-go | Unexplained failures. Fix and re-run - failed capacities sort to the front of the next run |
| Rollback | None needed. Rules on a deactivated policy set do nothing, and a re-run overwrites them |

## Phase 4 - Review gate

Run: Fabric Pol - MIG_ActivateAllCapacityPolicySets with mode Report (optional, as a smell test). Nothing else.

This is the decision point, and the reason the phases are separate. Activation puts rule 1 into force, so every workspace not in rule 2 or rule 3 loses the ability to create governed items. The question to answer and sign off is:

How many workspaces will lose the ability to create items, on which capacities?

Per capacity:

live workspaces under the Node    ubsppcoe_Workspace, _ubsppcoe_nodeid_value = the Node, ubsppcoe_statecode eq 1
  - ubsppcoe_workspacecount       in rule 2, stamped in Phase 3
  - ubsppcoe_exceptioncount       in rule 3, stamped in Phase 3
= workspaces that will be denied

The first number is not stamped anywhere; it needs a query against ubsppcoe_Workspace per capacity, counting every live workspace whatever its OAP flag. A workspace that is both OAP-enabled and excepted is subtracted twice, so treat the result as a lower bound where exceptions exist.

ubsppcoe_rulecount alone is not the answer. rulecount = 1 is right for an unused capacity and catastrophic for a live one where the OAP flag was never rolled out; rulecount > 1 can still deny 498 of 500 workspaces.

| Signal | Action |
| --- | --- |
| ubsppcoe_lastrebuild empty, or ubsppcoe_lasterror populated | Blocker. Phase 3 did not complete for that capacity. Fix and re-run Phase 3 |
| Denied = 0 | Activate |
| Denied is small and nameable | Have the platform team OAP-enable those workspaces, or add Policy Exceptions rows. Re-run Phase 3, then activate |
| Denied is large, across many capacities | Stop. Whether ubsppcoe_oapenabled rollout is complete enough to enforce on is a decision above this project |

The Report mail lists each candidate capacity with its rule, whitelisted-workspace and exception counts. Look first for many rules and few whitelisted workspaces. It cannot show total workspaces per Node, so it is a smell test, not the sign-off.

| Go | Denial figures per capacity written down and agreed by the accountable owner (To confirm: who signs - the sources say only that a large denial needs a decision above this project), and the activation date announced |
| --- | --- |
| No-go | No written agreement, or any blocker row |
| Rollback | None needed - nothing has changed |

## Phase 5 - Activate

This is the only step that changes access. Announce it before you run it.

Run: Fabric Pol - MIG_ActivateAllCapacityPolicySets. The mode input is required: type Report or Activate (case does not matter). Anything else terminates the run before a row is read.

5.1 Dry run - mode Report.

- Run it. It makes no Fabric call and no Dataverse write - check the run history shows the Activate action skipped.

- Read the DRY RUN mail. Is the count what Phase 4 led you to expect? Candidates are rows with Status = Inactive, a policy set and ubsppcoe_rulecount of 1 or more. Capacities with rulecount = 1 are included and will activate with rule 1 alone; Phase 4 is the only thing that stops a total lock on a live capacity. The dry-run mail text may still say "a rule count greater than 1" - the filter, not that sentence, decides (To confirm whether the built flow's wording was corrected).

- If DeleteCapacityPolicySet was not on since Phase 1, check the candidate list by hand against Node rows soft-deleted since registration - this query cannot see ubsppcoe_Node.

5.2 First tranche - mode Activate, about five capacities. Cancel from the run history after about five, then on one of them:

- Policy set shows Active in the portal

- Its Capacity Policies row shows Status = Active and ubsppcoe_lasterror empty

- A governed item created in a whitelisted (OAP) workspace - allowed

- A governed item created in a non-whitelisted workspace - refused

- If the holder workspace sits on this capacity, an item created in it - allowed (the Phase 2 exception working)

The two creation tests are the acceptance test for the whole project. Stop here if either is wrong - five capacities is recoverable; two hundred is an incident.

5.3 The rest - mode Activate to completion. Expect about 20 minutes per 200 capacities: the flow waits 6 seconds after each activation to stay under the tenant-wide limit of 10 activations a minute. Do not try to speed it up.

5.4 Read the activation mail. It is sent on every live run, clean or not, and is the record of when the estate went under enforcement. Failed capacities stay Inactive with the reason in ubsppcoe_lasterror and are not enforced. The likeliest cause is missing Capacity Admin. Fix and re-run: only rows still Inactive are picked up, and an already-active set (400 PolicySetAlreadyActive) counts as activated.

| Go | Acceptance tests passed on the first tranche; final run's failure list empty or every entry understood |
| --- | --- |
| No-go | Either creation test wrong on the first tranche |
| Rollback | Per capacity: deactivate the policy set and set ubsppcoe_status back to Inactive (section 4.2) |

## Phase 6 - Verify

Run: nothing new. Read Capacity Policies directly, or through Fabric Pol - ListCapacityPolicySets.

- Every migrated capacity present, Status = Active, ubsppcoe_lastrebuild recent, ubsppcoe_lasterror empty

- Three capacities spot-checked in the portal: rule 1 present, rule 2 copies consistent with ubsppcoe_workspacecount

- A workspace from the exceptions list can still create any item type on its capacity

- Nobody is reporting refusals they should not be getting

| Go | All four checks pass |
| --- | --- |
| No-go | Unexpected refusals - use the emergency procedure in section 4.3, then find the cause |
| Rollback | As Phase 5, per capacity |

## Phase 7 - Clean up

- Turn the four Dataverse-triggered BAU flows back on: Fabric Pol - InitializeCapacityPolicySet, Fabric Pol - AddWorkspaceToPolicy, Fabric Pol - RemoveWorkspaceFromPolicy and Fabric Pol - RebuildOnExceptionChange. This is the moment business as usual starts - from here, row changes publish themselves.

- Run Fabric Pol - MIG_RebuildAllCapacityPolicies once more (on, Run, off) and confirm every ubsppcoe_lastrebuild moved. It is the only estate-wide check there is, and it picks up any OAP flag, Node move or exception change made while the event flows were off.

- Check for capacities added during the window. The rebuild only covers capacities already in Capacity Policies. To confirm: a ubsppcoe_Node row added while InitializeCapacityPolicySet was off is not expected to be replayed when the flow is turned on, so compare Node rows created since Phase 1 (and the noNode list) against Capacity Policies, and ask the platform team to re-save any missing row so the BAU flow fires.

- Delete the three disposable MIG_ flows - turn off, then delete Fabric Pol - MIG_RegisterAllCapacityPolicySets, Fabric Pol - MIG_InitializeCapacityPolicySet and Fabric Pol - MIG_ActivateAllCapacityPolicySets. Do this only after Phase 6 is signed off.

- Hand over what is outstanding: the Phase 1 noNode list to the platform team; the Phase 4 denial figures and who signed them; every capacity activated at rulecount = 1 and whether it is genuinely unused or awaiting OAP rollout.

| Go | Event flows on, final rebuild clean, three MIG_ flows deleted, hand-over sent |
| --- | --- |
| Rollback | Turning an event flow off again is safe. A deleted MIG_ flow cannot be restored and would have to be rebuilt from scratch |

# 4. Rollback and emergency

## 4.1 If you have to stop halfway

| Stopped after | State | What is enforced |
| --- | --- | --- |
| Phase 1, 2, 3 or 4 | Policy sets exist, with or without rules, all deactivated | Nothing |
| Phase 5, partway | Some capacities Active | Only the activated ones |

Stopping before Phase 5 is free - leave it, or delete the policy sets and rows. Stopping partway through Phase 5 is stable, not broken: activated capacities are governed, the rest are as they were. Re-run mode Activate to finish, or roll back the activated ones.

Do not leave Phase 5 part-done and walk away. While the event flows are off, nothing keeps activated capacities current. If Phase 5 pauses for more than a day, run MIG_RebuildAllCapacityPolicies before stopping and again before resuming.

## 4.2 Undoing activation for one capacity

- Deactivate the policy set with the Fabric REST call POST /v1/workspaces/{holder}/policySets/{id}/deactivate, made as the workspace provisioning service account (see the Architecture document section 8), where {holder} is the holder workspace ID and {id} the policy set ID. To confirm: how this call is made in practice must be agreed before Phase 5 (section 2.5 E3).

- Set that capacity's ubsppcoe_status back to Inactive in Capacity Policies, so a re-run of Phase 5 picks it up again.

Deactivated, the policy set enforces nothing and its rules stay published, so re-activating later needs no rebuild.

## 4.3 Emergency - people are blocked

Use 4.2 for each affected capacity, then find the cause (see the Error handling and monitoring guide section 6). Two things not to do:

- Do not delete the policy set. It loses the registration and makes recovery a re-run of the whole migration for that capacity.

- Do not delete rules to unlock. A policy with zero rules is unenforced, and the next rebuild silently re-locks it.

| Symptom | Likely cause |
| --- | --- |
| Whole capacity locked, rulecount = 1 | No workspace on it has ubsppcoe_oapenabled = true - a Phase 4 miss |
| One workspace refused, others fine | Not whitelisted or excepted, or its Node points elsewhere |
| Everything refused across many capacities | Policy Item Types mis-seeded |
| Every Fabric call failing 400/404 | PolicyApiBeta pointing the wrong way for the API's release stage |

# 5. After cutover

| Component | State after cutover |
| --- | --- |
| Fabric Pol - MIG_RegisterAllCapacityPolicySets | Deleted. No BAU role |
| Fabric Pol - MIG_InitializeCapacityPolicySet | Deleted. Unsafe standalone - it has no eligibility check |
| Fabric Pol - MIG_ActivateAllCapacityPolicySets | Deleted. New capacities are activated one at a time by InitializeCapacityPolicySet |
| Fabric Pol - MIG_RebuildAllCapacityPolicies | Kept, switched off - the only estate-wide repair tool. Turn on, Run, turn off |
| Fabric Pol - InitializeCapacityPolicySet, AddWorkspaceToPolicy, RemoveWorkspaceFromPolicy, RebuildOnExceptionChange | Switched on in Phase 7 |
| Fabric Pol - DeleteCapacityPolicySet, RebuildCapacityPolicyRules, ListCapacityPolicySets | On, unchanged |

New capacities no longer need this guide. A row added to ubsppcoe_Node triggers InitializeCapacityPolicySet, which creates, registers, rebuilds and activates that capacity on its own - including the capacities on the Phase 1 noNode list, once the platform team adds their rows.

Nothing converges the estate on its own, and nothing observes it. A failed event flow, a workspace moved between Nodes, a hard-deleted exception row or a hand-edited rule all persist until someone runs MIG_RebuildAllCapacityPolicies, and a policy set deactivated or deleted outside the flows is not detected at all. Both are open design questions; the Error handling and monitoring guide section 4 describes how to catch them.

# 6. Sign-off checklist

| # | Phase | Check | Evidence | Signed by / date |
| --- | --- | --- | --- | --- |
| 1 | 0 | Section 2 complete: four event flows off, DeleteCapacityPolicySet and RebuildCapacityPolicyRules on, account, permissions, tables, seven variables, duplicate names, leftovers | Checklist |  |
| 2 | 0 | Holder-workspace placement decided (governed or not) | Note |  |
| 3 | 1 | Compose_eligible_count matches the expected estate | Run history |  |
| 4 | 1 | First tranche: no rules, not activated, Node populated, Status = Inactive | Portal, table |  |
| 5 | 1 | Failed empty; noNode list handed to the platform team | Report mail |  |
| 6 | 2 | Policy Exceptions seeded, holder row first, all Active = Yes, no EXAMPLE rows | Table |  |
| 7 | 3 | Every row has ubsppcoe_lastrebuild, ubsppcoe_lasterror empty; rule 3 seen where expected | Table, portal |  |
| 8 | 4 | Per-capacity denial figures written down and agreed | Sign-off record |  |
| 9 | 5 | Report dry-run count matches Phase 4 | Dry-run mail |  |
| 10 | 5 | First tranche acceptance test: OAP workspace allowed, non-OAP workspace refused, holder workspace allowed | Test record |  |
| 11 | 5 | Full activation run; failures resolved or accepted | Activation mail |  |
| 12 | 6 | All migrated capacities Active, no errors; exceptions still work; no unexpected refusals | Table, portal |  |
| 13 | 7 | Event flows on; final MIG_RebuildAllCapacityPolicies run clean; no capacity added during the window left unregistered | Table |  |
| 14 | 7 | Three MIG_ flows deleted; MIG_RebuildAllCapacityPolicies kept, off | Solution |  |
| 15 | 7 | Hand-over sent: noNode list, Phase 4 figures, rulecount = 1 activations | Mail |  |

# 7. Related documents

| Document | What it covers |
| --- | --- |
| The Architecture document | The solution, the three rules, identity and the Fabric REST calls, and section 5 - what each MIG_ flow does |
| The Deployment guide | Everything that must be deployed before Phase 0, including the tables, the seed list of item types, the exceptions list and the environment variables |
| The Error handling and monitoring guide | Business as usual after cutover: failure handling, monitoring, common errors and the emergency unlock |